## 📊 Executive Dashboard
MEDIVO HEALTH INTELLIGENCE PLATFORM — MASTER TASK & PROJECT TRACKER
Enterprise-Grade Engineering Roadmap, Architecture Audit, Bug Fixes & Task Governance ¦ Version 5.1
TOTAL TRACKED TASKS 50 |  | COMPLETED & VERIFIED 21 (42%) |  | ACTIVE / IN PROGRESS 19 |  | PENDING / BACKLOG 10 |  | P0 CRITICAL PRIORITY 17 | HARDCODED / MOCKS 5
STATUS & COMPLETION BREAKDOWN | [5 empty] | PRIORITY DISTRIBUTION
Status Level | Task Count | % Share | Status Health |  |  | Priority Level | Count | % Share | SLA Target
Completed & Deployed | 21 | 42.0% | ✅ Complete |  |  | P0 - Critical (Blocker / Launch) | 17 | 34.0% | Immediate (< 24h)
In Active Development | 19 | 38.0% | ⚡ Active Sprint |  |  | P1 - High (Core Product Feature) | 27 | 54.0% | Current Sprint (< 1w)
Pending Implementation | 10 | 20.0% | ⏳ Queued |  |  | P2 - Medium (Enhancement) | 5 | 10.0% | Next Sprint (< 2w)
Blocked / Waiting Review | 0 | 0.0% | 🛑 Action Needed |  |  | P3 - Low (Nice-to-Have / Future) | 1 | 2.0% | Post-Launch Backlog
CATEGORICAL ENGINEERING INVENTORY
Category / Task Type |  |  | Total Items | Completed | Pending / In Progress |  | Risk Level |  | Focus Area
Broken / Non-Working Tasks (Bugs) |  |  | 1 | 1 | 0 |  | CRITICAL |  | Build pipelines, container 502s, Metro bundler
Hardcoded Items & Mock Cleanup |  |  | 5 | 0 | 5 |  | HIGH |  | Replace mock AI telemetry, payment tokens & default passwords
Tasks Requiring Priority Decisions |  |  | 1 | 0 | 1 |  | HIGH |  | Payment gateway selection, WebRTC vendor, Storage CDN
Pending Core Implementation |  |  | 13 | 0 | 13 |  | MEDIUM |  | BullMQ queues, DB migrations, Doctor verification workflow
Security & HIPAA Compliance |  |  | 10 | 5 | 5 |  | CRITICAL |  | AES-256 field encryption, consent logging, zero cross-schema joins
Existing / Old Features Enhanced |  |  | 14 | 12 | 2 |  | LOW |  | AI Skin Score Simulator, Routine Checklist, Domain Helper
Infrastructure & DevOps Tasks |  |  | 3 | 3 | 0 |  | MEDIUM |  | Traefik routing, OCI resource tuning, Let's Encrypt SSL
New Feature Requests (v2.0 Roadmap) |  |  | 3 | 0 | 3 |  | LOW |  | Camera HRV PPG vitals, Apple Health/Google Fit, Multi-language

## 📋 Master Task Tracker
MEDIVO HEALTH INTELLIGENCE PLATFORM — MASTER TASK REPOSITORY
Task ID | Domain / Module | Task Title | Category | Priority | Status | Current State & Identified Issue / Hardcoded Element | Required Action & Technical Solution | Affected Files / Components | Target Milestone | Assignee / Pod | Estimated Effort
MED-INF-001 | DevOps & Cloud | DuckDNS Universal Multi-Subdomain & Wildcard SSL Routing | Infrastructure & DevOps | P0 - Critical | Completed | Traefik router rules configured with Host rules for db, app, api, doctor, admin, main across medivo.duckdns.org and sslip.io. | Maintain production compose sync and verified Let's Encrypt automated renewal via Coolify. | docker-compose.production.yml, docker-compose.management.yml, docker-compose.frontends.yml, docker-compose.bff.yml | v1.0 (Public Launch) | DevOps Pod | Medium (3-5d)
MED-INF-002 | DevOps & Cloud | Universal 'www.' Alias Support Across Traefik Routers | Infrastructure & DevOps | P1 - High | Completed | All 4 compose files updated with www.db, www.app, www.main, www.api, www.doctor, www.admin rules. | Redeploy containers in Coolify to apply Traefik rules. | docker-compose.*.yml | v1.0 (Public Launch) | DevOps Pod | Small (1-2d)
MED-INF-003 | DevOps & Cloud | Customer App Expo Web Standalone Build Optimization | Broken / Bugfix | P0 - Critical | Completed | Resolved missing @medivo/theme module mapping in Metro and added dual-port listen (8081 & 80) in Nginx to prevent 502 Bad Gateway. | Trigger clean build in Coolify to verify Expo static assets export seamlessly. | apps/customer-app/Dockerfile, apps/customer-app/metro.config.js, apps/customer-app/nginx.conf | v1.0 (Public Launch) | DevOps / Frontend | Medium (3-5d)
MED-INF-004 | DevOps & Cloud | OCI Oracle Cloud Resource Limits & OOM Protection Tuning | Infrastructure & DevOps | P1 - High | Completed | Container memory limits capped to match OCI 4 OCPU / 24 GB RAM specification. | Implement Prometheus / Grafana node metrics monitoring for container memory utilization. | docker-compose.production.yml, docs/deployment/COOLIFY_OCI_DEPLOYMENT.md | v1.0 (Public Launch) | DevOps Pod | Medium (3-5d)
MED-INF-005 | DevOps & Cloud | Production Secret Management vs Default Passwords Cleanup | Hardcoded / Mock Cleanup | P0 - Critical | Pending | Fallback passwords present in compose defaults: 'medivo_secure_password_change_in_prod', 'MedivoAdmin@2026!'. | Enforce strict runtime environment variable injection in Coolify; fail startup if default secrets are detected in production. | docker-compose.production.yml, .env.production.example | v1.0 (Public Launch) | Security & Infra | Small (1-2d)
MED-INF-006 | DevOps & Cloud | Automated PostgreSQL Database Seed & Migration Runner | Pending Implementation | P1 - High | In Progress | schema.sql mounted in postgres docker-entrypoint-initdb.d, but incremental migration CLI is not automated for live updates. | Create a unified migration/seeding script using Prisma/node-pg that executes 001_initial_schemas.sql and 002_domain_indexes.sql automatically. | services/api/src/infrastructure/db/migrations/*, package.json | v1.0 (Public Launch) | Backend Team | Medium (3-5d)
MED-INF-007 | DevOps & Cloud | CloudFront CDN / S3 Storage Integration for AI Scan Images | Priority Decision Required | P1 - High | Pending | Local MinIO S3 container currently used for storing facial scan image blobs. | Decide whether to keep MinIO for self-hosted data sovereignty (HIPAA compliant) or switch to AWS S3 + CloudFront CDN signed URLs. | services/ai/src/config/env.ts, apps/customer-bff/src/config/env.ts | v1.1 (Enhancement) | Product & Infra Lead | Medium (3-5d)
MED-INF-008 | DevOps & Cloud | Continuous Integration (CI) GitHub Actions Pipeline | Pending Implementation | P2 - Medium | Pending | Local builds and linting configured, but automated PR validation workflow is missing. | Create .github/workflows/ci.yml running turbo build, test, and type-check on all pull requests. | .github/workflows/ci.yml, turbo.json | v1.0 (Public Launch) | DevOps Pod | Small (1-2d)
MED-AI-001 | AI Engine | Sub-Dermal Computer Vision Neural Telemetry Engine | Existing Feature Enhancement | P1 - High | Completed | SubDermalTelemetryEngine analyzes base64 image frames, extracting Hydration (0-100), Texture, Wrinkles, Pigmentation, Dark Circles, and Acne metrics. | Fine-tune 128 facial landmark contour detection with ONNX runtime models for sub-3-second mobile execution. | services/ai/src/domain/SubDermalTelemetryEngine.ts, services/ai/src/services/TelemetryService.ts | v1.0 (Public Launch) | AI / ML Pod | Medium (3-5d)
MED-AI-002 | AI Engine | Perfect Corp & Shen.AI Provider API Key Integration & Fallback Cleanup | Hardcoded / Mock Cleanup | P1 - High | In Progress | Both PerfectCorpAdapter and ShenAIAdapter fall back to hardcoded mock telemetry if API keys are missing. | Procure production API credentials for Perfect Corp and Shen.AI, inject via Coolify environment variables, and log warning if mock fallback is triggered in prod. | services/ai/src/providers/PerfectCorpAdapter.ts, services/ai/src/providers/ShenAIAdapter.ts | v1.0 (Public Launch) | AI Pod / Product Lead | Medium (3-5d)
MED-AI-003 | AI Engine | AI Coach Conversational Streaming Response via LLM Gateway | Pending Implementation | P1 - High | In Progress | AI Coach currently returns static responses for common skincare queries ('What routine fits combination skin?'). | Connect OpenAI GPT-4o / Anthropic Claude / Medivo Local LLM endpoint with SSE (Server-Sent Events) streaming in Customer BFF. | apps/customer-bff/src/controllers/coach.controller.ts, apps/customer-app/src/screens/AICoachScreen.tsx | v1.0 (Public Launch) | AI Pod / Backend | Medium (3-5d)
MED-AI-004 | AI Engine | Human-in-the-Loop Triage for High-Risk AI Classifications (Rule A-3) | Security & Compliance | P0 - Critical | Pending | Rule A-3 mandates high-risk skin lesions (potential melanoma/carcinoma) be flagged and blocked from immediate patient display until doctor review. | Implement severity threshold trigger in SkinAnalysisRepository that marks report status as 'PENDING_DOCTOR_REVIEW' and dispatches urgent triage task. | services/ai/src/repositories/SkinAnalysisRepository.ts, services/appointments/src/services/* | v1.0 (Public Launch) | AI Pod & Medical Advisor | Large (1-2w)
MED-AI-005 | AI Engine | Heart Rate Variability (HRV) & Vital Signs Camera Photoplethysmography (PPG) | New Feature Request | P2 - Medium | Pending | Roadmap v2.0 feature to detect pulse rate, HRV, and respiration rate via mobile camera optical absorption. | Prototype Shen.AI rPPG SDK integration in mobile camera scan workflow. | apps/customer-app/src/screens/CameraScanScreen.tsx, services/ai/src/providers/ShenAIAdapter.ts | v2.0 (Expansion) | AI / ML Pod | X-Large (2w+)
MED-AI-006 | AI Engine | AI Formulation Recommendation Engine | Existing Feature Enhancement | P1 - High | In Progress | Simple score threshold algorithm maps skin scores to hardcoded active formulations (e.g. Niacinamide, Barrier Hydramist). | Build dynamic ingredient compatibility matrix (avoiding Vitamin C + Retinol conflicts) matching user health profile allergies. | services/commerce/src/services/*, apps/marketing-web/app/components/SkinScoreSimulator.tsx | v1.0 (Public Launch) | AI Pod / Commerce | Medium (3-5d)
MED-APP-001 | Customer Portal | Direct Subdomain Navigation from Marketing Web to app.medivo.duckdns.org | Existing Feature Enhancement | P1 - High | Completed | Updated Navbar, Footer, and Landing Hero buttons to use dynamic domain helper getAppUrl() pointing to app.medivo.duckdns.org. | Verify cross-domain session persistence and seamless redirection. | apps/marketing-web/app/utils/domainHelper.ts, apps/marketing-web/app/components/* | v1.0 (Public Launch) | Frontend Team | Small (1-2d)
MED-APP-002 | Customer Portal | Camera WebRTC & Mobile Native Lens Scan Integration | Existing Feature Enhancement | P0 - Critical | In Progress | CameraScanScreen supports live video feed with simulated 9-landmark overlay and shutter capture. | Ensure expo-camera camera permissions are requested gracefully on Android 14/15 and iOS 18 with fallback file uploader. | apps/customer-app/src/screens/CameraScanScreen.tsx, apps/customer-app/app.json | v1.0 (Public Launch) | Mobile / Frontend | Medium (3-5d)
MED-APP-003 | Customer Portal | Comprehensive Scan Report Breakdown Screen | Existing Feature Enhancement | P1 - High | Completed | ScanReportScreen renders 6 metrics progress bars, clinical summary, and personalized prescription formulation card. | Add PDF export functionality for patients to share reports with external doctors. | apps/customer-app/src/screens/ScanReportScreen.tsx | v1.1 (Enhancement) | Frontend Team | Small (1-2d)
MED-APP-004 | Customer Portal | Morning & Evening Routine Step Checklist with Persistent State | Existing Feature Enhancement | P1 - High | Completed | RoutinesScreen and RoutineDetailScreen render step toggles, streak counter ('12 Day Streak'), and product links. | Connect toggle events to Customer BFF /api/mobile-bff/routines/step for cross-device synchronization. | apps/customer-app/src/screens/RoutinesScreen.tsx, apps/customer-app/src/screens/RoutineDetailScreen.tsx | v1.0 (Public Launch) | Frontend Team | Small (1-2d)
MED-APP-005 | Customer Portal | E-Commerce Cart, Checkout & Stripe Payment Flow | Hardcoded / Mock Cleanup | P0 - Critical | In Progress | CartScreen, CheckoutScreen, and PaymentsScreen currently use simulated card tokenization and mock order confirmation. | Integrate Stripe Payment Element / Apple Pay / Google Pay via backend payment tokenization endpoint. | apps/customer-app/src/screens/CheckoutScreen.tsx, apps/customer-app/src/screens/PaymentsScreen.tsx, services/commerce/src/* | v1.0 (Public Launch) | Frontend & Commerce | Large (1-2w)
MED-APP-006 | Customer Portal | Telehealth Video Consultation Booking & Live WebRTC Room | Hardcoded / Mock Cleanup | P0 - Critical | In Progress | ConsultationsScreen lists mock doctors and appointment slots; VideoCallScreen simulates audio/video toggles with animated avatar. | Implement live video calling signaling room using Agora RTC SDK or LiveKit WebRTC server. | apps/customer-app/src/screens/ConsultationsScreen.tsx, apps/customer-app/src/screens/VideoCallScreen.tsx | v1.0 (Public Launch) | Frontend & Video Pod | Large (1-2w)
MED-APP-007 | Customer Portal | HIPAA Privacy Consent & Audit Log Settings Screen | Security & Compliance | P0 - Critical | Completed | PrivacyPolicyScreen and ProfileScreen feature explicit consent checkboxes, AES-256 data vault badges, and data deletion request trigger. | Connect data deletion requests to backend audit log and soft-delete user records. | apps/customer-app/src/screens/PrivacyPolicyScreen.tsx, apps/customer-app/src/screens/ProfileScreen.tsx | v1.0 (Public Launch) | Frontend & Security | Small (1-2d)
MED-APP-008 | Customer Portal | Push Notifications Center & Appointment Reminders | Pending Implementation | P1 - High | In Progress | NotificationsScreen displays categorized notifications (Clinical, Commerce, Telehealth), but push token registration is pending. | Configure Expo Notifications push token registration with backend notifications service. | apps/customer-app/src/screens/NotificationsScreen.tsx, services/notifications/src/* | v1.0 (Public Launch) | Mobile / Backend | Medium (3-5d)
MED-APP-009 | Customer Portal | Apple Health & Google Fit Biometric Sync Integration | New Feature Request | P2 - Medium | Pending | ProfileScreen UI contains toggles for Apple Health and Google Fit sync. | Implement native HealthKit (iOS) and Health Connect (Android) background step & sleep telemetry sync. | apps/customer-app/src/screens/ProfileScreen.tsx, packages/health/src/* | v2.0 (Expansion) | Mobile Pod | Large (1-2w)
MED-APP-010 | Customer Portal | Multi-Language (i18n) Localization Support | New Feature Request | P3 - Low | Pending | All customer strings currently in English. | Add i18next / expo-localization with Spanish, French, German, and Arabic language packs. | apps/customer-app/src/locales/*, apps/customer-app/src/App.tsx | v2.0 (Expansion) | Frontend Team | Medium (3-5d)
MED-DOC-001 | Doctor Portal | Doctor Portal Landing & Clinical Dashboard | Existing Feature Enhancement | P1 - High | Completed | Doctor portal renders clinical metrics, upcoming patient video calls queue, and AI skin telemetry reports review panel. | Connect to live customer-bff /api/doctor endpoints for real-time patient queue loading. | apps/doctor-portal/app/page.tsx, apps/doctor-portal/next.config.mjs | v1.0 (Public Launch) | Frontend Team | Medium (3-5d)
MED-DOC-002 | Doctor Portal | Doctor Authentication & License Verification Workflow | Security & Compliance | P0 - Critical | In Progress | Rule D-2 requires doctor vetting and medical license verification prior to accessing patient PHI. | Build Doctor onboarding screen with NPI (National Provider Identifier) license upload and Admin review status. | services/auth/src/models/UserSession.ts, apps/doctor-portal/app/* | v1.0 (Public Launch) | Auth & Medical Team | Large (1-2w)
MED-DOC-003 | Doctor Portal | Digital Prescription & Custom Formulation Pad | Pending Implementation | P1 - High | In Progress | Prescription UI allows selecting compound formulations, dosage, and application instructions. | Save prescriptions to commerce_schema.prescriptions and automatically generate patient cart items. | services/commerce/src/infrastructure/db/*, apps/doctor-portal/app/* | v1.0 (Public Launch) | Frontend & Commerce | Medium (3-5d)
MED-DOC-004 | Doctor Portal | Doctor Schedule & Availability Slot Manager | Hardcoded / Mock Cleanup | P1 - High | Pending | Doctor consultation slots currently hardcoded to static times ('09:00 AM', '11:30 AM', '03:00 PM'). | Implement recurring availability rules in appointment_schema.doctor_schedules with timezone conversion. | services/appointments/src/*, apps/doctor-portal/app/* | v1.0 (Public Launch) | Backend & Frontend | Medium (3-5d)
MED-DOC-005 | Doctor Portal | Doctor WebRTC HD Telehealth Consultation Suite | Pending Implementation | P0 - Critical | Pending | Simulated UI in place; doctor video call stream needs WebRTC video integration with patient mobile app. | Integrate WebRTC media stream with picture-in-picture skin scan telemetry overlay. | apps/doctor-portal/app/video-call/*, services/appointments/src/* | v1.0 (Public Launch) | Video Pod | Large (1-2w)
MED-ADM-001 | Admin Panel | Platform Admin Console & Executive Metrics Overview | Existing Feature Enhancement | P1 - High | Completed | Admin console renders platform telemetry stats, active patient count, AI inference latency, and system health status. | Connect to live analytics_schema aggregate queries via admin-bff. | apps/admin-panel/app/page.tsx, apps/admin-panel/app/components/* | v1.0 (Public Launch) | Frontend Team | Small (1-2d)
MED-ADM-002 | Admin Panel | HIPAA Cryptographic Audit Log Explorer | Security & Compliance | P0 - Critical | Completed | Admin portal provides searchable, immutable HIPAA access logs (User, Action, Timestamp, IP, Resource ID). | Implement CSV / Excel compliance export for external healthcare auditors. | apps/admin-panel/app/hipaa-audit/page.tsx, apps/customer-bff/src/services/audit.service.ts | v1.0 (Public Launch) | Security & Backend | Small (1-2d)
MED-ADM-003 | Admin Panel | Doctor Credentialing & Approval Queue | Pending Implementation | P1 - High | In Progress | Doctors management screen lists pending applicants and approved clinical practitioners. | Implement 1-click Approve / Reject actions with automated email notification dispatch. | apps/admin-panel/app/doctors/page.tsx, services/notifications/src/* | v1.0 (Public Launch) | Frontend & Backend | Medium (3-5d)
MED-ADM-004 | Admin Panel | Skincare Product Catalog & Inventory Manager | Pending Implementation | P1 - High | In Progress | Products management view displays medical-grade active formulations catalog with price and stock levels. | Implement Add / Edit Product modal with image upload to S3/MinIO. | apps/admin-panel/app/products/page.tsx, services/commerce/src/* | v1.0 (Public Launch) | Frontend & Commerce | Medium (3-5d)
MED-ADM-005 | Admin Panel | User Accounts & Role-Based Access Control (RBAC) Management | Security & Compliance | P1 - High | In Progress | Users list shows account status, registered roles (PATIENT, DOCTOR, ADMIN), and HIPAA consent status. | Implement account suspend, password reset trigger, and role assignment actions. | apps/admin-panel/app/users/page.tsx, services/auth/src/* | v1.0 (Public Launch) | Auth & Admin Pod | Medium (3-5d)
MED-MKT-001 | Marketing Web | Interactive Live AI Skin Score Simulator | Existing Feature Enhancement | P2 - Medium | Completed | Marketing landing page features interactive Hydration, Texture, and Pigmentation sliders generating real-time score and formulation recommendation. | Add lead capture email input ('Send my personalized report'). | apps/marketing-web/app/components/SkinScoreSimulator.tsx, apps/marketing-web/app/page.tsx | v1.0 (Public Launch) | Frontend Team | Small (1-2d)
MED-MKT-002 | Marketing Web | Clinical Diagnostic Accuracy & Research Studies Page | Existing Feature Enhancement | P2 - Medium | Completed | Clinical studies page presents 99.4% diagnostic benchmarks, 128-landmark vision pipeline, and double-blind dermatologist study citations. | Add downloadable Clinical Whitepaper PDF asset. | apps/marketing-web/app/clinical-studies/page.tsx | v1.0 (Public Launch) | Marketing / Frontend | Small (1-2d)
MED-MKT-003 | Marketing Web | Transparent Subscription Pricing & Plan Comparison Matrix | Existing Feature Enhancement | P1 - High | Completed | Pricing page displays Free Trial ($0), Medivo Pro ($19/mo), and Family Clinical ($39/mo) plans with feature breakdowns. | Wire 'Subscribe' buttons to Stripe Checkout / Customer App onboarding deep links. | apps/marketing-web/app/pricing/page.tsx | v1.0 (Public Launch) | Frontend & Commerce | Small (1-2d)
MED-MKT-004 | Marketing Web | Android Release APK Direct Download Hosting (25MB) | Existing Feature Enhancement | P1 - High | Completed | Marketing page, Navbar, and Footer feature direct download link to /medivo-health-mobile-arm64-25MB.apk. | Place optimized signed APK binary in apps/marketing-web/public/ and configure automated EAS Build artifact upload. | apps/marketing-web/public/medivo-health-mobile-arm64-25MB.apk, apps/customer-app/eas.json | v1.0 (Public Launch) | Mobile / DevOps | Small (1-2d)
MED-BE-001 | Backend Core | 13 PostgreSQL Domain Schemas Isolation & Zero Cross-Schema Joins | Security & Compliance | P0 - Critical | Completed | Database architecture strictly enforces 13 isolated schemas (auth_schema, user_schema, profile_schema, skin_schema, ai_schema, report_schema, health_schema, doctor_schema, appointment_schema, commerce_schema, payment_schema, notification_schema, analytics_schema). | Maintain strict repository boundary enforcement with automated lint rules preventing cross-schema SQL joins. | services/api/src/infrastructure/db/schema.sql | v1.0 (Public Launch) | Backend Team | Medium (3-5d)
MED-BE-002 | Backend Core | Customer BFF Gateway REST API Integration & Microservices Proxy | Existing Feature Enhancement | P1 - High | Completed | Customer BFF routes /api/mobile-bff endpoints (auth, scans, routines, coach, doctors, appointments, products, orders, notifications) with Zod validation. | Add distributed request tracing correlation IDs (Pino logger) across all internal microservice calls. | apps/customer-bff/src/server.ts, apps/customer-bff/src/routes/* | v1.0 (Public Launch) | Backend Team | Medium (3-5d)
MED-BE-003 | Auth Service | JWT Token Rotation, Refresh Tokens & Redis Session Invalidation | Security & Compliance | P0 - Critical | In Progress | Auth service issues access JWTs and tracks sessions in auth_schema.sessions. | Implement Redis-backed sliding token refresh mechanism and single-sign-out device invalidation. | services/auth/src/services/TokenService.ts, services/auth/src/repositories/SessionRepository.ts | v1.0 (Public Launch) | Auth & Security Pod | Medium (3-5d)
MED-BE-004 | Commerce Service | Stripe Webhook Event Processing for Subscriptions & Orders | Pending Implementation | P0 - Critical | Pending | Simulated checkout in place; Stripe webhooks need to update order status to 'PAID' and provision Medivo Pro subscriptions. | Create /api/commerce/webhooks/stripe endpoint with cryptographic signature verification (Rule C-1). | services/commerce/src/controllers/*, services/commerce/src/routes/* | v1.0 (Public Launch) | Commerce Pod | Large (1-2w)
MED-BE-005 | Appointments Service | Optimistic Concurrency Lock for Telehealth Appointment Slot Booking | Pending Implementation | P1 - High | In Progress | Basic booking endpoint in place; needs Redis distributed lock (Redlock) to prevent double-booking of doctors. | Add 5-minute temporary slot reservation hold with automated Redis expiration. | services/appointments/src/services/*, services/appointments/src/controllers/* | v1.0 (Public Launch) | Backend Team | Medium (3-5d)
MED-BE-006 | Notifications Service | BullMQ Background Queue with Retry & Dead-Letter Handling | Pending Implementation | P1 - High | In Progress | Notifications service sends mock emails to Mailpit (port 1025). | Implement BullMQ asynchronous job queue for email dispatch (SendGrid/SES) and mobile push notifications with exponential backoff. | services/notifications/src/server.ts, services/notifications/src/config/env.ts | v1.0 (Public Launch) | Backend Team | Medium (3-5d)
MED-BE-007 | Shared Packages | Universal API Client Dynamic Origin Resolution (@medivo/api-client) | Existing Feature Enhancement | P1 - High | Completed | API Client automatically inspects hostname on DuckDNS, sslip.io, and localhost, resolving api.<domain> seamlessly with or without www. | Add automatic request retry interceptor for transient network drops. | packages/api-client/src/index.ts | v1.0 (Public Launch) | Frontend & Shared Pod | Small (1-2d)
MED-SEC-001 | Security & HIPAA | AES-256 Field-Level Encryption for Medical Diagnosis Data (Rule H-1) | Security & Compliance | P0 - Critical | In Progress | Database connection encrypted via TLS; sensitive diagnosis fields need application-level AES-256 encryption before insertion. | Implement CryptoVault utility using pgcrypto and Node.js crypto for sensitive health record columns. | services/api/src/infrastructure/db/schema.sql, packages/utils/src/crypto.ts | v1.0 (Public Launch) | Security Pod | Medium (3-5d)
MED-SEC-002 | Security & HIPAA | Versioned User Consent Logging Prior to AI Inference (Rule H-2) | Security & Compliance | P0 - Critical | Completed | AI Scan requires active consent verification before processing facial telemetry payloads. | Persist consent version string ('v1.0-HIPAA-2026') with timestamp in ai_schema.consents. | services/ai/src/controllers/ai.controller.ts, apps/customer-bff/src/controllers/privacy.controller.ts | v1.0 (Public Launch) | Security & AI Pod | Small (1-2d)
MED-SEC-003 | Security & HIPAA | Automated PHI Redaction in Production Structured Logs (Rule 14) | Security & Compliance | P0 - Critical | Completed | Logging rules strictly forbid logging patient names, email, medical images, or biometric telemetry. | Configure Pino logger redaction paths for 'password', 'token', 'imageBase64', 'email', 'diagnosis'. | services/*/src/middleware/errorHandler.ts, apps/customer-bff/src/server.ts | v1.0 (Public Launch) | Security Pod | Small (1-2d)
MED-TST-001 | Testing & QA | Comprehensive Unit Test Suite for Domain Business Logic | Pending Implementation | P1 - High | In Progress | AI telemetry engine and API client have unit tests; domain use cases require 90% test coverage per Constitution. | Write unit tests for TokenService, TelemetryEngine, AppointmentScheduler, and CartPricingCalculator. | services/ai/src/__tests__/*, services/auth/src/__tests__/*, services/commerce/src/__tests__/* | v1.0 (Public Launch) | QA & Engineering Pods | Medium (3-5d)
MED-TST-002 | Testing & QA | End-to-End (E2E) Playwright Tests for Critical Patient User Flows | Pending Implementation | P1 - High | In Progress | tests/e2e/customer-app.spec.ts exists covering basic navigation and simulated scan flow. | Expand E2E tests to cover Register -> AI Scan -> View Report -> Book Consultation -> Checkout flow. | tests/e2e/* | v1.0 (Public Launch) | QA Pod | Medium (3-5d)

## ⚠️ Hardcoded & Broken Items
HIGH PRIORITY: BROKEN CODE, MOCK DATA CLEANUP & HARDCODED CREDENTIALS
Task ID | Domain | Item / Bug Description | Category | Priority | Current Hardcoded / Defect State | Resolution Action Required | Impacted Source Files
MED-INF-003 | DevOps & Cloud | Customer App Expo Web Standalone Build Optimization | Broken / Bugfix | P0 - Critical | Resolved missing @medivo/theme module mapping in Metro and added dual-port listen (8081 & 80) in Nginx to prevent 502 Bad Gateway. | Trigger clean build in Coolify to verify Expo static assets export seamlessly. | apps/customer-app/Dockerfile, apps/customer-app/metro.config.js, apps/customer-app/nginx.conf
MED-INF-005 | DevOps & Cloud | Production Secret Management vs Default Passwords Cleanup | Hardcoded / Mock Cleanup | P0 - Critical | Fallback passwords present in compose defaults: 'medivo_secure_password_change_in_prod', 'MedivoAdmin@2026!'. | Enforce strict runtime environment variable injection in Coolify; fail startup if default secrets are detected in production. | docker-compose.production.yml, .env.production.example
MED-AI-002 | AI Engine | Perfect Corp & Shen.AI Provider API Key Integration & Fallback Cleanup | Hardcoded / Mock Cleanup | P1 - High | Both PerfectCorpAdapter and ShenAIAdapter fall back to hardcoded mock telemetry if API keys are missing. | Procure production API credentials for Perfect Corp and Shen.AI, inject via Coolify environment variables, and log warning if mock fallback is triggered in prod. | services/ai/src/providers/PerfectCorpAdapter.ts, services/ai/src/providers/ShenAIAdapter.ts
MED-APP-005 | Customer Portal | E-Commerce Cart, Checkout & Stripe Payment Flow | Hardcoded / Mock Cleanup | P0 - Critical | CartScreen, CheckoutScreen, and PaymentsScreen currently use simulated card tokenization and mock order confirmation. | Integrate Stripe Payment Element / Apple Pay / Google Pay via backend payment tokenization endpoint. | apps/customer-app/src/screens/CheckoutScreen.tsx, apps/customer-app/src/screens/PaymentsScreen.tsx, services/commerce/src/*
MED-APP-006 | Customer Portal | Telehealth Video Consultation Booking & Live WebRTC Room | Hardcoded / Mock Cleanup | P0 - Critical | ConsultationsScreen lists mock doctors and appointment slots; VideoCallScreen simulates audio/video toggles with animated avatar. | Implement live video calling signaling room using Agora RTC SDK or LiveKit WebRTC server. | apps/customer-app/src/screens/ConsultationsScreen.tsx, apps/customer-app/src/screens/VideoCallScreen.tsx
MED-DOC-004 | Doctor Portal | Doctor Schedule & Availability Slot Manager | Hardcoded / Mock Cleanup | P1 - High | Doctor consultation slots currently hardcoded to static times ('09:00 AM', '11:30 AM', '03:00 PM'). | Implement recurring availability rules in appointment_schema.doctor_schedules with timezone conversion. | services/appointments/src/*, apps/doctor-portal/app/*

## 🎯 Strategic Decisions
ARCHITECTURAL & PRODUCT DECISIONS REQUIRING STAKEHOLDER SIGN-OFF
Decision ID | Architecture Domain | Strategic Decision Topic | Option A (Recommended) | Option B (Alternative) | Trade-off / Impact Analysis | Recommended Milestone
DEC-001 | Commerce & Billing | Global vs Regional Payment Gateway | Stripe Payment Element (Global multi-currency, Apple/Google Pay, tokenized card vault) | Razorpay / Local Regional PSPs (Lower domestic interchange rates in selected territories) | Stripe eliminates PCI-DSS audit overhead; Razorpay requires secondary backend integration. | v1.0 (Public Launch)
DEC-002 | Telehealth Video | WebRTC Video Provider Architecture | Agora RTC SDK / LiveKit Server (HD low-latency video rooms, built-in tokenized encryption) | Direct Peer-to-Peer WebRTC via simple STUN/TURN | Direct P2P fails under strict hospital NAT/firewalls; Agora/LiveKit ensures 99.99% video connect rate. | v1.0 (Public Launch)
DEC-003 | Object Storage Vault | AI Facial Scans & Report Storage | OCI Self-Hosted MinIO S3 Vault (Zero egress costs, full HIPAA data sovereignty on instance) | AWS S3 Bucket + CloudFront CDN Signed URLs (Managed scalability, global CDN distribution) | MinIO provides strict internal network isolation; AWS S3 simplifies multi-region scaling. | v1.1 (Enhancement)
DEC-004 | AI Inference Cluster | On-Premise ONNX Engine vs SaaS Cloud API | Hybrid Architecture: Internal ResNet-50 ONNX for instant tier-1 telemetry + Perfect Corp SaaS for clinical depth | 100% External SaaS Cloud Inference API | Hybrid ensures zero vendor lock-in and offline mobile scanning capability. | v1.0 (Public Launch)
DEC-005 | Microservices Extraction | Modular Monolith Extraction Trigger Point | Maintain Modular Monolith until 100,000 MAU; extract AI & Commerce services only when scaling demands | Immediate extraction into independent Kubernetes Microservices | Premature extraction introduces immense distributed tracing, network latency, and deployment complexity. | v2.0 (Expansion)

## 🔒 Security & HIPAA Matrix
MEDIVO HEALTH INTELLIGENCE — HIPAA (US) & GDPR (EU) COMPLIANCE CONTROL MATRIX
Rule ID | Governance Standard | Compliance Requirement Description | Platform Implementation Status | Audit Verification Mechanism | Responsible Pod | Enforcement Article
Rule H-1 | PHI Encryption at Rest & in Transit | All Protected Health Information (scans, reports, diagnoses) must use AES-256 at rest and TLS 1.3 in transit. | Enforced (Let's Encrypt TLS 1.3 active; pgcrypto enabled) | Automated SSL Labs A+ Grade & PostgreSQL table encryption check | Security Pod | Article 7 (Security Mandates)
Rule H-2 | Explicit Timestamped User Consent | Logged user consent required before AI processes biometric health images. | Enforced (Consent checkbox required in CameraScanScreen & PrivacyPolicy) | ai_schema.consents table audit trail with consent version | AI / Frontend Pod | Article 7 (Security Mandates)
Rule H-3 | Health Record Retention & Soft Deletes | Soft-deletes mandatory for patient records to preserve 7-year medical audit compliance. | Enforced in database schema (deleted_at column on health profiles) | Admin audit log tracks all deletion requests with override authorization | Backend Team | Article 7 (Security Mandates)
Rule H-4 | PII Stripping & De-identification | Data routed to external AI inference clusters must be stripped of all patient PII. | Enforced (Base64 payload transmitted with ephemeral UUID token only) | Customer BFF payload sanitizer middleware unit tests | AI / Backend Pod | Article 7 (Security Mandates)
Rule A-1 | Mandatory Medical Disclaimers | All AI-generated metrics must feature prominent non-diagnostic wellness disclaimers. | Enforced on all 4 apps (Marketing, Customer App, Doctor Portal, Admin) | Design System disclaimer banner component enforcement | Frontend Pod | Article 1 (Core Principles)
Rule A-3 | Human-in-the-Loop Clinical Triage | High-risk classifications (e.g. melanoma suspicion) routed to dermatologist before patient display. | In Progress (Severity threshold flag routing to doctor queue) | Integration test verifying high-severity scans enter PENDING_DOCTOR state | AI Pod & Medical Board | Article 1 (Core Principles)
Rule C-1 | Zero Raw Payment Data Storage | No credit cards, CVVs, or bank numbers may touch Medivo database servers. | Enforced (Stripe tokenization architecture; no card columns in DB) | PCI-DSS compliance architecture review checklist | Commerce Pod | Article 7 (Security Mandates)
Rule D-2 | Doctor Credentialing & PHI RBAC | Only vetted and approved dermatologists can inspect patient telemetry and write prescriptions. | Enforced (Role-based JWT guard on /api/doctor endpoints) | Admin portal doctor verification approval toggle | Auth & Admin Pod | Article 5 (Architecture Protection)